Estimate of Story Points for Sprint 2:  
  
From Sprint 1, without specifically stating that we could complete 38 story points, the total of user stories we assigned to sprint 1 included 38 story points. By the end of the sprint we’d completed 25 story points and assigned 2 more, so we have 15 story points left not completed.

The 15 story points were from user stories that, while not completed, had been broken into tasks and some of those tasks had been completed.  
  
For Sprint 2, we estimated the number of story points at 23 because some of the story points from sprint 1 were counted even though they were not directly related to production work. We corrected this on sprint 2 by not counting story points for project planning and management or for team development. While these tasks still required significant effort they did not earn story points in sprint 2.

These are the User Stories and tasks we scheduled for Sprint 2:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Work Item Type | Title 1 | Title 2 | Story Points |
| 83 | User Story | Profile Engagement Sensitivity |  | 3 |
| 179 | Task |  | explore how the firebase cometchat showcases last activity |  |
| 220 | Task |  | Reference that in a local object |  |
| 158 | User Story | Matching Algorithm Spr2 : Machine Learning/Advanced Matching |  | 5 |
| 159 | Task |  | investigate potential available ML builds |  |
| 160 | Task |  | incorporate weightage of implicit interests |  |
| 161 | User Story | Create New User Profile/Account Spr2 |  | 3 |
| 139 | Task |  | Profile - Outdoor Interests and Activities |  |
| 192 | Task |  | Add Page - User can set up personal profile |  |
| 203 | Task |  | Design Profile Parameters and Answer Lists |  |
| 204 | Task |  | Create a link to the DB from putting and getting User Profile Parameters |  |
| 162 | User Story | SSO Authentication Spr2 |  | 3 |
| 178 | Task |  | Create Facebook App |  |
| 201 | Task |  | Implement Facebook Configuration |  |
| 207 | Task |  | Log in with Google SSO |  |
| 163 | User Story | User Interface Implementation spr2 - Dashboard |  | 5 |
| 164 | User Story | | Accept Match Spr2 | 2 |
| 165 | User Story | | Decline Match Spr2 | 2 |
| 193 | Task |  | User Matches Interface |  |
| 194 | Task |  | Chat Interface |  |
| 197 | Task |  | Build Header and Navigation Bar |  |
| 205 | Task |  | User Dashboard Design Options |  |
| 206 | Task |  | Build My Outdoorsies / Friends Interface |  |
| 166 | User Story | Sprint 2 Planning and Management |  |  |
| 167 | Task |  | Create Burndown Chart for Sprint 2 on Dashboard |  |
| 168 | Task |  | Decompose Stories into Tasks |  |
| 169 | Task |  | Define Acceptance Criteria for User Stories |  |
| 170 | Task |  | Define Tests for Work Items as appropriate |  |
| 171 | Task |  | Groom User Stories and Ordering - Sprint 2 |  |
| 172 | Task |  | Plan Sprint 2 Goal and Scope |  |
| 173 | Task |  | Sprint 1 Review and Retrospective |  |
| 174 | Task |  | Sprint 2 Review and Retrospective |  |
| 175 | Task |  | Put together all components of submission for Sprint 1 per rubric |  |
| 185 | Bug | Change favicon and app name that appears in browser window or tabs |  |  |
| 208 | Test Case | User Chooses Authentication Method and Creates an account and profile |  |  |
|  |  |  |  |  |
|  |  |  |  | 23 |